## Flood Alleviation
Flood Alleviation Programme
Flood Alleviation Schemes mitigating flood risk associated with the surface water network of streams, rivers and culverts
Status Report - May 2022
Project Name | Description | May 2022 Status
Deansgrange ECFRAM Flood Storage Scheme | Flood Risk Management works on the Deansgrange Stream. | The Deansgrange Study is at the stage where flood alleviation options are being finalised. A cost benefit assessment is also being carried out on the identified options. A second public enganegemnet event is planned in Q3 2022 when the options assessment is completed.
Carrickmines/Shanganagh Flood Storage Scheme | Flood Risk Management works on the Carrickmines/Shanganagh/Loughlinstown Rivers. | Consultants have been appointed for the flood risk management works. Surveying contracts have been completed including topographical surveys and flow/rainfall surveys. Initial modelling work is completed and very early options are being considered. A site investigation contract is due to commence in June 2022 and a Newsletter will be issued at that time