## Flood Alleviation
Flood Alleviation Programme
Flood Alleviation Schemes mitigating flood risk associated with the surface water network of streams, rivers and culverts
Status Report - February 2020
Project Name | Description | February 2020 Status
Deansgrange ECFRAM Flood Storage Scheme | Flood Risk Management works on the Deansgrange Stream. | The assessment has been completed and an award has been made mid November. Data gathering is underway.
Carrickmines/Shanganagh Flood Storage Scheme | Tenders are currently being prepared for Engineering and Environmental Consultants for the Carrickmines/Shanganagh Rivers. | Tenders were received February 14th and are being assessed.
Kilbogget Park Flood Storage | Upgrade of the culvert screen and creation of online flood storage area in the environs of the constructed wetlands | Project is now subsumed into OPW Scheme . Detailed design nearing completion. Tendering for construction to commence in March 2020.
Dundrum Slang Integrated Catchment Model | Preparation of Flood Risk maps and development of alleviation options | Topographical survey completed. Model build completed. Draft Flood maps received and being reviewed.
Ballinteer M50 Jn 13 Environs Flood Storage | Assess feasibility of enhancing flood storage | Discussions ongoing with TII.
Carysfort Maretimo Integrated Catchment Model | Preparation of Flood Risk maps and development of alleviation options | Tendering to commence Q2 2020.