## Road Map 2018 to 19
ROAD MAP FOR WATER SERVICES PROJECTS - to be posted to the Capital Programme Section of the Website
Updated July 2018
Name of Project | SPRING | WINTER | SUMMER
| 2018 | 2018/2019 | 2019
Corbawn Coastal Protection Works | Tendering complete. Pre-award process underway | Construction Complete Quarter 3, 2019
Ardglas Screen Upgrade | Design underway | Public Consultation Process | Commence Construction Quarter 4, 2019
Cabinteely Park Flood Storage | Preliminary Design Underway | Preliminary Design Complete | Commence Construction Quarter 3, 2019
Fernhill Park Flood Storage | Commence Design | Tendering Process | Commence Construction Quarter 3, 2019
Kilbogget Park Flood Storage | Part 8 Consultation | Design Stage | Commence Construction Quarter 3, 2019
Marlay Park Enhanced Flood Storage |  | Engage Consultants/Design Stage/Public Consultation Process | Commence Construction Quarter 4, 2019
Watsons Estate Pipeline Rehabilitation | Scoping | Commence Construction Quarter 4, 2018
Glenavon Park Flood Storage Online Attenuation | Liaison onging with Office of Public Works
Bray Landfill Coastal Defence | Design underway | Part 8 Consultation Complete
Ballinteer M50 Jn 13 Environs Flood Storage | Commence Design | Commence Construction Quarter 4, 2018 Complete Design
Carysfort Maretimo Integrated Catchment Model | Scoping | Tendering Complete | Model Completed
Dundrum Slang Integrated Catchment Model | Brief Preparation | Flow + Rainfall Survey Underway | Model Completed
Mulvey Park Screen Upgrade | Tendering Process | Commence Construction Quarter 4, 2018
Commons Road Coarse Screen | Tendering Process | Commence Construction Quarter 4, 2018