## Flood Alleviation
Flood Alleviation Programme
Flood Alleviation Schemes mitigating flood risk associated with the surface water network of streams, rivers and culverts
Status Report - September 2020
Project Name | Description | September 2020 Status
Deansgrange ECFRAM Flood Storage Scheme | Flood Risk Management works on the Deansgrange Stream. | This project is well underway with the hydraulic model now complete. Alleviation options are being considered and a virtual Public Information Day is planned for end September
Carrickmines/Shanganagh Flood Storage Scheme | Tenders are currently being prepared for Engineering and Environmental Consultants for the Carrickmines/Shanganagh Rivers. | This project has now commenced and data gathering is underway.
Kilbogget Park Flood Storage | Upgrade of the culvert screen and creation of online flood storage area in the environs of the constructed wetlands | This project has been awarded. Construction is due to commence on site in October.
Dundrum Slang Integrated Catchment Model | Preparation of Flood Risk maps and development of alleviation options | Final flood maps have been received.
Ballinteer M50 Jn 13 Environs Flood Storage | Assess feasibility of enhancing flood storage | Discussions ongoing with TII.
Carysfort Maretimo Integrated Catchment Model | Preparation of Flood Risk maps and development of alleviation options | Project on hold due to funding constraints.