## Sheet1
Flood Alleviation Programme
Flood Alleviation Schemes mitigating flood risk associated with the surface water network of streams, rivers and culverts
Status Report - December 2023
Project Name | Description | December 2023 Status
Deansgrange ECFRAM Flood Alleviation Scheme | Flood Risk Management works on the Deansgrange Stream. | The Deansgrange Project is currently at the Part 8 Public Consultation stage and it is planned to bring a report the December 2023 Council meeting.
Carrickmines/Shanganagh Flood Alleviation Scheme | Flood Risk Management works on the Carrickmines/Shanganagh/Loughlinstown Rivers. | All survey and site investigation works are now complete. River modelling work is alos completed and a preferred option has been presented by the project consultants. Engagement is underway with key stakeholders directly impacted by the preferred option. A second public engagement event is scheduled for mid December to present the preferred option to stakeholders.