## Sheet1
Flood Alleviation Programme
Flood Alleviation Schemes mitigating flood risk associated with the surface water network of streams, rivers and culverts
Status Report - April 2024
Project Name | Description | December 2023 Status
Deansgrange ECFRAM Flood Alleviation Scheme | Flood Risk Management works on the Deansgrange Stream. | The project received Part 8 Planning approval at the December Council meeting subject to a separate SuDS assessment being carried out in the catchment. The Council now await a determination from ABP as to whether a full EIA is required.
Carrickmines/Shanganagh Flood Alleviation Scheme | Flood Risk Management works on the Carrickmines/Shanganagh/Loughlinstown Rivers. | The preferred option was presented to stakeholders at a public engagement event in December 2023. The Options Report is being updated to incorporate comments, where appropriate. Final environmental surveys are currently being completed and a Part 10 Planning submission will be sent to ABP in Q3 2024.