## Capital Dashboard Jan 2022
| Tick when Updated on capital dashboard | Order on website | Project Approval Status on Dashboard | Job code | Project Name on Dashboard | Directorate | Not Committed Expenditure (outstanding commitment on Agresso) | Actual Expenditure from start of scheme to end December 2021 ( Euro column) | Actual & Committed Expenditure from start of scheme to end December 2021( Commited column on Agresso) | Status of Project | Capital Budget 2020-22 | Budget Variance | Comment
Appendix 1 |  |  |  | C32LY029 | Kilbogget Park Online Attenuation (2) C32LY029 | Municipal Services | 0.06 | 1987 | 2047 | Merged with Deansgrange project
Appendix 2 |  | 1 | Not Contractually Committed | C32LY032 | Flood Alleviation Ardglas Screen Upgrade & Design | Municipal Services | 26384 | 23807 | 50190 | Works on Hold. | 0.1 | 0.5 | Detailed Design
|  | 2 | Not Contractually Committed | C32LY034 | Flood Alleviation Carysfort Maretimo Integrated Catchment Model | Municipal Services | 5074 | 9902 | 14975 | Project on Hold pending direction from the OPW. | 0.226 | 0.213 | Project On Hold
|  | 3 | Not Contractually Committed | C32LY034 | Flood Alleviation Carysfort Maretimo Stream - Dart Culvert Assessment | Municipal Services | 0.005 | 0.001 | 0.001 | Assessment completed. Works recommended - no start date. | 0.234 | 0.233 | Project on Hold
|  | 4 |  | C32LY028 | Flood Alleviation - Deansgrange ECFRAM | Municipal Services | 284422 | 1593874 | 1878295 | The Deansgrange Study is well under way with alleviation options being considered. A cost benefit assessment is underway on the identified options. An initial public engagement has taken place. A ground investigation has commenced. The advance contract , Kilbogget Park Flood Storage Contract is nearing completion. This will provide some element of flood relief to properties downstream, particularly in the Bayview Seafield environs however additional works are still required to provide the desired level of protection. | 2.264 | 0 | This code is renamed as Deansgrange ECFRAM on the Dashboard and updated. It includes expenditure related to Kilbogget Park and Glenavon Park Flood Storage. Ensure line on order 400318608 linked to C32LY028 is closed. New line entered with new code. Project Summary on J Drive to be updated. Ask FMS to update the Financial Details tab on the Dashboard.
|  | 5 | Not Contractually Committed | C32LY030 | Flood Alleviation Marlay PK Flood Storage Feasability Study | Municipal Services | 0 | 6900 | 6900 | On hold | 0.2 | 0.0193 | Preliminary Design
|  | 6 | This is contractually committed | C32LY036 | Flood Alleviation - Monkstown Flood Risk Assesssment | Municipal Services | 50538 | 16134 | 66672 | The topographical survey is competed and a CCTV and Flow and Rainfall Survey is being Tendered at present. | 0.15 | 0.15 | Preliminary Design
|  | 7 | Not Contractually Committed | New Code to be set up. Currently charged to C32LY010 | Flood Alleviation Sandyford Park Flood Storage | Municipal Services | 11012 | 1039254 | 1050266 | Project on hold pending direction from the OPW. | 1 | 0.984 | Proposed (Pre feasibility)
|  | 8 | Not Contractually Committed | C32F0072 | Flood Alleviation - Carrickmines/Shanganagh Flood Relief Scheme (Loughlinstown ECFRAM ) | Municipal Services | 492427 | 547024 | 1039451 | Consultants have been appointed for the flood risk management works. A flow/rainfall survey has been completed and topographical surveying contracts have commenced. Initial modelling is underway. | 0.55 | 0 | This code is renamed as Loughlinstown ECFRAM on the Dashboard and updated. It currently includes expenditure related to Cabinteely Park Flood Storage. Project Summary on J Drive to be updated Ask FMS to update the Financial Details tab on the Dashboard.
[7 empty] | 869857.005 | 3236895.001 | 4106749.001